## SUMMARY (hidden)
SUMMARY OF RENEWABLE ENERGY (RE) PROJECT APPLICATIONS under the RE ACT of 2008
as of 31 DECEMBER 2021
RESOURCES | APPLICATIONS IN-PROCESS |  | POTENTIAL CAPACITY MW |  | On-going Evaluation |  | Withdrawn | Qualified-for preparation of documents | Qualified -for pre-signing of Applicant | Endorsed for award | Awarded
| Commercial | Own-Use | Commercial | Own-Use | with DOE | with Applicant
Hydropower | 11 | - | - | - | 4 | 3 |  | 1 | 9 |  | 1
Ocean Energy | - | - | - | -
Geothermal | - | - | - | - |  |  |  | 2
Wind | 15 | - | 13690 | - | 1 |  |  | 2 (conversion to new RESC)
Solar | 12 | - | 4115.804 | - | 1 |  |  |  |  | 7 (6 conversion to SEOC; 1 SESC)
Biomass | - | - | - | - |  | 1 | 1 |  |  | 2 | 2
TOTAL | 38 | 0 | 17805.804 | 0 | 34

## BEOC (hidden)
BIOMASS ENERGY OPERATING CONTRACT APPLCATIONS
as of 15 April 2020
PROJECT PROFILE | [14 empty] | COMPANY PROFILE | [6 empty] | CONTRACT PROFILE | [10 empty] | FINANCIAL COMMITMENT
|  |  | LOCATION | [7 empty] | CAPACITY |  |  |  |  | CONTACT DETAILS | [16 empty] | COST OF INVESTMENT |  |  | SIGNING FEE |  |  | PERFORMANCE BOND |  | DEVELOPMENT ASSISTANCE FUND | [5 empty] | TRAINING FUND
ITEM NO. | Date of Application | PROJECT NAME | ON GRID/ OFF GRID | ISLAND / GRID | REGION | PROVINCE | CITY / MUNICIPALITY | BARANGAY | LOCATION | ORIGINAL CONTRACT AREA (Has.) | POTENTIAL CAPACITY (MW) | INSTALLED CAPACITY (MW) | THERMAL CAPACITY (MW) | RDF CAPACITY (MT/day) | COMPANY NAME | CONTACT PERSON | DESIGNATION | COMPANY ADDRESS | CONTACT NO. | FAX NO. | EMAIL ADDRESS | CONTRACT NO. | CERTIFICATE OF REGISTRATION NO. | DATE AWARDED | NATURE OF CONTRACT / STAGE OF CONTRACT | MODE OF AWARDING | DATE OF DECLARATION OF COMMERCIALITY | CERTIFICATE OF CONFIRMATION OF COMMERCIALITY | TARGET TESTING & COMMISSIONING DATE | TARGET COMMERCIAL OPERATION DATE | ACTUAL COMMERCIAL OPERATION DATE | TERM (Yrs.) | PRE-DEV. COMMITMENT (PhP) YEAR 1 | PRE-DEV. COMMITMENT (PhP) YEAR 2 | DEV. COST OF INVESTMENT (USD/MW) | SIGNING FEE (Php) | DATE OF PAYMENT | O.R. NUMBER | AMOUNT (Php) | EXPIRY DATE | PRE-DEV D.A. (Php) | D.A. UTILIZATION (Php) | D.A. BALANCE (Php) | DEV D.A. (Php) | D. A. UTILIZATION (Php) | D.A. BALANCE (Php) | PRE-DEV. TF (Php) | DEV. TF TRAINING (Php) | PROJECT STATUS | REMARKS | STATUS OF COMPLIANCES | STATUS (or ACTION TAKEN) | ISSUES AND CONCERNS | ACTION TAKEN | RECOMMENDATION | CONTRACT STATUS | DATE OF TERMINATION | GROUNDS FOR TERMINATION | STATUS
1 | 2019-11-21 | Surallah Biogas Ventures Corporation |  | MINDANAO | XII |  |  |  | Brgy. Tubi-allah, Surallah, South Cotabato |  | 0.764 |  |  |  | Surallah Biogas Ventures Corporation | [36 empty] | Endorsement to award of BEOC; endorsed to LS on 28 April 2020
2 | 2019-11-21 | Surallah Biogas Ventures Corporation |  | MINDANAO | XII |  |  |  | Brgy. Cannery, Polomolok, South Cotabato |  | 2.3 |  |  |  | Surallah Biogas Ventures Corporation | [36 empty] | Endorsement to award of BEOC; endorsed to LS on 28 April 2020 | Endorsement to award of BEOC; endorsed to RELSD on 28 April 2020 | Endorsement to award of BEOC; endorsed to RELSD on 28 April 2020 | Endorsement to award of BEOC; endorsed to RELSD on 28 April 2020 | Endorsement to award of BEOC; endorsed to RELSD on 28 April 2020 | Endorsement to award of BEOC; endorsed to RELSD on 28 April 2020 | Endorsement to award of BEOC; endorsed to RELSD on 28 April 2020 | Endorsement to award of BEOC; endorsed to RELSD on 28 April 2020
3 | 2020-02-24 | Mindoro Harvest Energy Co., Inc. |  | LUZON | IV-B |  |  |  | Brgy. Nabuslot, Pinamalayan, Oriental Mindoro |  | 8 |  |  |  | Mindoro Harvest Energy Co., Inc. | [36 empty] | - Financially and legally qualified; Technically not qualified. - Granted request for extension to submit lacking/additional technical requirements after ECQ as per our letter dated 25 March 2020 | - Financially and legally qualified; Technically not qualified. - To submit additional/lacking documents - Granted request for extension to comply with the technical requirements due to ECQ | - Financially and legally qualified; Technically not qualified. - To submit additional/lacking documents - Granted request for extension to comply with the technical requirements due to ECQ | - Financially and legally qualified; Technically not qualified. - To submit additional/lacking documents - Granted request for extension to comply with the technical requirements due to ECQ | - Financially and legally qualified; Technically not qualified. - To submit additional/lacking documents - Granted request for extension to comply with the technical requirements due to ECQ | - Financially and legally qualified; Technically not qualified. - To submit additional/lacking documents - Granted request for extension to comply with the technical requirements due to ECQ | - Financially and legally qualified; Technically not qualified. - To submit additional/lacking documents - Granted request for extension to comply with the technical requirements due to ECQ | - Financially and legally qualified; Technically not qualified. - To submit additional/lacking documents - Granted request for extension to comply with the technical requirements due to ECQ

## GOC (hidden)
GEOTHERMAL OPERATING CONTRACT (GOC) APPLICATION |  | GEOTHERMAL OPERATING CONTRACT (GOC) APPLICATION
as of 15 April 2020 |  | as of 15 April 2020
Date Received (sent to Email due to ECQ) | Date Received by Unit | ISLAND/GRID | REGION | LOCATION | Applicant/ Requesting Party | Project Name | Type of Application (e.g., Endorsement, Service Contract, COC, TEC, etc.) | Area Verification | Orientation | Paid Processing/Application Fee |  |  |  | Remarks | Capacity
2020-04-03 | 2020-04-03 | LUZON | V | Sorsogon / Albay | Bacman Geothermal Inc. | Palayan Binary Geothermal Power Plant | Operating Contract | 2020-02-26 | 2020-03-12 | 2020-04-07 | dated 4/17/2020 received by REMB April 29, 2020 | dated 4/12/2020 received by REMB April 16, 2020 | 2020-04-16 | LS, FS and Technical evaluation results recommend to submit supplementary requirements. To send letter to BGI. | TBD
2020-04-03 | 2020-04-03 |  |  |  | Bacman Geothermal Inc. | Tanawon Geothermal Power Plant | Operating Contract | 2020-02-26 | 2020-03-12 | 2020-04-07 | dated 4/17/2020 received by REMB April 29, 2020 | dated 4/12/2020 received by REMB April 16, 2020 | 2020-04-16 | LS, FS and Technical evaluation results recommend to submit supplementary requirements. To send letter to BGI. | TBD

## SES.OC (hidden)
SOLAR ENERGY SERVICE CONTRACT/SOLAR ENERGY OPERATING CONTRACT APPLICATIONS
as of 31 March 2020
ITEM NO. | Date of Application | PROJECT NAME | ON GRID/ OFF GRID | ISLAND / GRID | REGION | LOCATION | POTENTIAL CAPACITY (MW) | COMPANY NAME | STATUS (or ACTION TAKEN) | STATUS | MINE
1 | 2018-06-13 | SM Seaside Mall Cebu Solar Power Project |  | Visayas | VII | Cebu City, Cebu | TBD | Solar Philippines Seasidemall Corporation | Endorsed to Award SESC; Solar Philippines expressed intent to sign SEOC unofficially | Awaiting submission of documentary requirements from SPIC | 6C | No letter
2 | 2018-08-22 | Paluan Solar Power Project |  | Luzon | IV-B | Paluan, Occidental Mindoro | TBD | Solar Para sa Bayan Corporation | Endorsed to Award SESC; Solar Philippines expressed intent to sign SEOC unofficially | Awaiting submission of documentary requirements from SPBC | 6C | No letter
3 | 2020-01-28 | 394kWp SM City BF Homes Paranaque RSPP |  | Luzon | NCR | Paranaque, Metro Manila | 0.39 | Solar Philippines Island Corporation | Endorsed to Award SESC; Solar Philippines expressed intent to sign SEOC unofficially | Awaiting submission of documentary requirements from SPIC | 6C | On process
4 | 2020-03-05 | SM Dasmariñas City RSPP |  | Luzon | IV-A | Dasmariñas City, Cavite | 0.6 | Solar Philippines Island Corporation | Endorsed to Award SESC; Solar Philippines expressed intent to sign SEOC unofficially | Awaiting submission of documentary requirements from SPIC | 6C | With letter
5 | 2020-03-05 | SM City Telabastagan Solar Power Project |  | Luzon | III | San Fernando, Pampanga | 0.54 | Solar Philippines Island Corporation | Endorsed to Award SESC; Solar Philippines expressed intent to sign SEOC unofficially | Awaiting submission of documentary requirements from SPIC | 6C | With letter
6 | 2020-01-14 | SM City Clark Solar Rooftop Project |  | Luzon | III | Clark, Pampanga | 1.31 | Solar Philippines Island Corporation | Endorsed to Award SESC; Solar Philippines expressed intent to sign SEOC unofficially | Awaiting submission of documentary requirements from SPIC | 6C | With letter
7 | 2019-09-13 | SM City Trece Martires Rooftop Solar Power Project |  | Luzon | IV-A | Trece Martires, Cavite | 0.6 | Solar Philippines Island Corporation | Endorsed to Award SESC; Solar Philippines expressed intent to sign SEOC unofficially | Awaiting submission of documentary requirements from SPIC | 6C | No letter
8 | 2019-12-27 | Tuy Batangas 2 Solar Power Project |  | Luzon | IV-A | Tuy and Balayan, Batangas | 62.5 | Greencore Power Solutions 2, Inc. | Endorsed to Award SESC; For endorsement to Award the SESC | On-going | 6 | On process
9 | 03 April 2020 (thru email) | Imus Solar Rooftop Power Project |  | Luzon | IV-A | Imus City, Cavite | TBD | Solar Pacific Citysun Corporation | Paid the application and processing fee. | For Legal, technical and financial evaluation of the application | 1 | With letter
Note |  | Acted during ECQ

## SEOC_P (hidden)
TYPE OF APPLICATION | SEOC Application
SOLAR ENERGY SERVICE CONTRACT (SEOC) APPLICATIONS as of 31 DECEMBER 2021
ISLAND | REGION | PROVINCE | PROJECT NAME | COMPANY NAME | POTENTIAL CAPACITY
Luzon | II | Cagayan | SolarAce3 Solar Power Plant Project | Solarace3 Energy Corp. | 200
| III | Bataan | Lucanin Solar Power Project | SMC Global Light and Power Corp. | 130.005
|  |  | Samal Solar Power Project | Samal Solar Renewable Energy, Corp. | 48.118
|  | Pampanga | Sabang Balen Solar 1 Power Project | Sapang Balen Solar Sustainable Energy Corp. | 91.1
|  | Zambales | San Marcelino Floating Solar Power Project | PV Sinag Power, Inc. | 144.73
|  |  | Botolan Solar Power Project | San Lorenzo Ruiz Piat Energy & Water, Inc. | 987.6
|  | Pampanga and Tarlac | Sapang Balen Solar 2 Power Project | Sapang Balen Solar Sustainable Energy Corp. | 463.995
| IV-A | Cavite | Vista Mall Daang Hari Solar Power Project | MSPECTRUM, INC. | 0.66
|  | Calamba City | 1.752 MW ATC Solar Power Rooftop Project | Laguna Rooftop Solar Corporation | 1.752
| IVA/IV-B | Occidental Mindoro and Batangas | Verde Island Passage (VIP) Off-shore WPP | Gigasol5, Inc. | 2000
| V | Camarines Norte | PAVI Green San Vicente Solar Power Plant Project | PAVI Green Renewable Energy, Inc. | 28.6
Luzon Total |  |  |  |  | 4096.56
Mindanao | X | Misamis Oriental | Misamis Solar Power Plant | Filinvest-ENGIE Renewable Energy Enterprise, Inc. | 19.244
Mindanao Total |  |  |  |  | 19.244
Grand Total |  |  |  |  | 4115.804

## WESC (hidden)
WIND ENERGY SERVICE CONTRACTS APPLCATIONS
as of 15 April 2020
PROJECT PROFILE | [14 empty] | COMPANY PROFILE | [6 empty] | CONTRACT PROFILE | [10 empty] | FINANCIAL COMMITMENT
|  |  | LOCATION | [7 empty] | CAPACITY |  |  |  |  | CONTACT DETAILS | [16 empty] | COST OF INVESTMENT |  |  | SIGNING FEE |  |  | PERFORMANCE BOND |  | DEVELOPMENT ASSISTANCE FUND | [5 empty] | TRAINING FUND
ITEM NO. | Date of Application | PROJECT NAME | ON GRID/ OFF GRID | ISLAND / GRID | REGION | PROVINCE | CITY / MUNICIPALITY | BARANGAY | LOCATION | ORIGINAL CONTRACT AREA (Has.) | POTENTIAL CAPACITY (MW) | INSTALLED CAPACITY (MW) | THERMAL CAPACITY (MW) | RDF CAPACITY (MT/day) | COMPANY NAME | CONTACT PERSON | DESIGNATION | COMPANY ADDRESS | CONTACT NO. | FAX NO. | EMAIL ADDRESS | CONTRACT NO. | CERTIFICATE OF REGISTRATION NO. | DATE AWARDED | NATURE OF CONTRACT / STAGE OF CONTRACT | MODE OF AWARDING | DATE OF DECLARATION OF COMMERCIALITY | CERTIFICATE OF CONFIRMATION OF COMMERCIALITY | TARGET TESTING & COMMISSIONING DATE | TARGET COMMERCIAL OPERATION DATE | ACTUAL COMMERCIAL OPERATION DATE | TERM (Yrs.) | PRE-DEV. COMMITMENT (PhP) YEAR 1 | PRE-DEV. COMMITMENT (PhP) YEAR 2 | DEV. COST OF INVESTMENT (USD/MW) | SIGNING FEE (Php) | DATE OF PAYMENT | O.R. NUMBER | AMOUNT (Php) | EXPIRY DATE | PRE-DEV D.A. (Php) | D.A. UTILIZATION (Php) | D.A. BALANCE (Php) | DEV D.A. (Php) | D. A. UTILIZATION (Php) | D.A. BALANCE (Php) | PRE-DEV. TF (Php) | DEV. TF TRAINING (Php) | PROJECT STATUS | REMARKS | STATUS OF COMPLIANCES | STATUS (or ACTION TAKEN) | ISSUES AND CONCERNS | ACTION TAKEN | RECOMMENDATION | CONTRACT STATUS | DATE OF TERMINATION | GROUNDS FOR TERMINATION | STATUS
1 | 2014-08-20 | Ilocos Norte Wind Power Project |  | Luzon | I |  |  |  | Burgos and Pasuquin, Ilocos Norte |  | TBD |  |  |  | Energy Development Corporation | [36 empty] | For preparation of WESC . Intent to sign the WESC under Omnibus Guidelines. | [6 empty] | On-going
2 | 2014-08-20 | Pasuquin WPP. |  | Luzon | I |  |  |  | Pasuquin, Ilocos Norte |  | TBD |  |  |  | Energy Development Corporation | [36 empty] | For preparation of WESC . Intent to sign the WESC under Omnibus Guidelines. | [6 empty] | On-going
3 | 2020-01-21 | Camiguin Wind Power Project |  | Mindanao | X |  |  |  | Mambajao, Mahinog, Guinsilaban, Sagay, and Catarman, Camiguin |  | 60 |  |  |  | Camigreen Inc. | [36 empty] | Legally and Financially pre-qualified. Technically not qualified. For preparation letter | [6 empty] | On-going

## WESC_P (hidden)
TYPE OF APPLICATION | WESC Application
WIND ENERGY SERVICE CONTRACT (WESC) APPLICATIONS as of 31 DECEMBER 2021
ISLAND | REGION | PROVINCE | PROJECT NAME | COMPANY NAME | POTENTIAL CAPACITY
Luzon | I | Ilocos Norte | Piddig-Carasi Wind Power Project | Caraballo Mountains UPC Asia Corporation | 440
|  | Cagayan and Ilocos Norte | Claveria Offshore Wind Farm Power Project | Domhain Earth Corp. | 0
| IV - A | Laguna and Quezon | Quezon Wind Power Project | Quezon Wind Energy Corp. | 0
|  |  | Laguna Wind Power Project | TOTALPower Inc. | 80
| IV-B | Occidental Mindoro | Calavite Passage Offshore Wind Project | Pililla AVPC Corporation | 1000
|  |  | Bulalacao One Onshore Wind Energy Project | CleanTech Global Renewables, Inc. | 330
|  | Occidental Mindoro and Oriental Mindoro | North Mindoro Offshore Wind Power Project | TOTALPower Inc. | 2100
|  | Oriental Mindoro, Occidental Mindoro and Antique | South Mindoro Offshore Wind Farm Project | Domhain Earth Corp. | 1300
|  | Provinces of Batangas and Occidental Mindoro | Calatagan Offshore Wind Farm | Domhain Earth Corp. | 1400
| IVA/IV-B | Occidental Mindoro and Batangas | VIP Offshore Wind Project Duplicate of Verde Island Passage (VIP) Off-shore WPP | Gigasol5, Inc. | 2000
Luzon Total |  |  |  |  | 8650
Visayas | VI | Guimaras and Negros Occidental | Negros Offshore Wind Power Project | wpd Philippines, Inc. | 500
|  | Sorosogon | Calintaan Island Wind Power Project | TOTALPower Inc. | 140
|  | Negros Occidental and Guimaras | Negros 2 Offshore Wind Power Project | wpd Philippines, Inc. | 500
|  | Offshore and Onshore of Guimaras | GS2 Offshore Wind Power Project | Vind Energy Corp. | 500
| VII | Negros Oriental | Negros Oriental Onshore and Offshore Wind Power Project | TOTALPower Inc. | 3400
Visayas Total |  |  |  |  | 5040
Grand Total |  |  |  |  | 13690

## HSC_P
remarks | application
HYDROPOWER ENERGY SERVICE CONTRACT (HSC) APPLICATIONS as of 31 DECEMBER 2021
ISLAND | REGION | PROVINCE | PROJECT NAME | COMPANY NAME | POTENTIAL CAPACITY
Luzon | CAR | Benguet | Irisan 1 | Hedcor, Inc. | 0
|  |  | San Roque West Pump Storage Hydroelectric Power Project | Strategic Power Development Corp. | 0
|  | Ifugao | Alimit HPP | SN Aboitiz Ifugao , Inc. | 0
|  |  | Alimit Pumped Storage HPP | SN Aboitiz Ifugao , Inc. | 0
| III | Nueva Ecija | Diaman | United Hydro Power Builders | 0
Mindanao | X | Misamis Oriental | Odiongan (Lower Cascade) | Oriental Energy and Power Generation Corporation | 0
|  |  | Odiongan (Middle Cascade) | Oriental Energy and Power Generation Corporation | 0
|  |  | Odiongan (Upper Cascade) | Oriental Energy and Power Generation Corporation | 0
| XI | Davao Oriental | Baganga River | Global Sibagat Hydro Power Corporation | 0
|  | Davao del Sur | Apo Agua | Apo Agua Infrastructura Inc. | 0
| XIII | Surigao del Sur | Calatngan HPP | King Energy Generation Inc. | 0
Grand Total |  |  |  |  | 0

## BEOC_P (hidden)
BIOMASS ENERGY SERVICE CONTRACT (BEOC) APPLICATIONS as of 30 SEPTEMBER 2021
Island | Region | Location | Project Name | Company | Potential Capacity
Luzon | IV-B | Brgy. Tubtub, Brooke’s Point, Palawan | 3.5-MW Biomass Power Plant Project | Brooke's Point Power Generation, Inc. | 3.5
Luzon Total |  |  |  |  | 3.5
Mindanao | XIII | Brgy. San Jose, Bislig, Surigao Del Sur | 50-MW Lumino Cogen Biomass Power Plant Project | Lumino Biomass Power Inc. | 50
Mindanao Total |  |  |  |  | 50
Grand Total |  |  |  |  | 53.5

## GSC_P (hidden)
TYPE OF APPLICATION | GSC Application
GEOTHERMAL ENERGY SERVICE CONTRACT (GSC) APPLICATIONS as of 30 SEPTEMBER 2021
ISLAND | REGION | PROVINCE | PROJECT NAME | COMPANY NAME | POTENTIAL CAPACITY (MW)
LUZON | CAR | Kalinga, Mountain Province | Mainit-Sadanga Geothermal Power Project | Energy Development Corp. | 0
LUZON Total |  |  |  |  | 0
Grand Total |  |  |  |  | 0